## Product Backlog
Project Name: |  | GAM125 - Sprint Backlog
Casters N Blasters
Team Member (Full Name) | Team Role / Interests | Sprint Information
Dillan Bullock | Balance Team and Lead | Sprint Number: | 3
Isaiah Oba | Balance and Art Team
Gabriella Godfrey | Art Team | Days In Sprint: | 1
Kara Beretto | Art Team
William Molette | Balance Team and Lead | Sprint Dates: | 11/25/2019 - 12/8/2019
Greg Marshall | Balance Team
Task (to-do) | Description / Notes | Assigned To (Team Member) | Est. Time (Hours) | Total Hours: | 100
Enemy Desgin | Design more detailed enimies well as concept art | Greg,Will,Gabriella | 15
Combat System | Tweak and Balance the combat system. | Will,Dillan,Gaberiella ,Isaiah | 20
Rule Book | Design rules fore the game and proof read them as well as adding more rules | Dillan,Gabriella | 5
Board art | Desgin board art | Kara,Gabriella | 10
3d printing and modeling | 3d modeling for game board player and enemy pieces | Kara,Gabriella | 20
Card art | design card art for front and back of cards | Will, Gaberilla, Greg | 20
Item art | draw the art for items and weapons in the gme | Kara,Gabriella | 10